## Project
Total Project Tracking - Parking Building Management System (PBMS)
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Initiation | Project Scoping | System | Define PBMS requirements, hardware limits, and core features | Nguyễn Duy Hiếu | Done | Sprint 1 | 01-Jun-2026 | Finalised project scope and DB schema
2 | Design | UI/UX Prototyping - Driver | Driver | Figma prototype for Driver mobile web portal | Nguyễn Quang Huy | Done | Sprint 1 | 05-Jun-2026 | Completed wireframes and color scheme
3 | Design | UI/UX Prototyping - Staff/Manager | Staff/Manager | Figma prototype for desktop monitoring dashboard | Trần Thái Bình | Done | Sprint 1 | 08-Jun-2026 | Completed layout of slot map and KPI charts
4 | Design | Architecture & DB Setup | System | Setup PostgreSQL schema with proper indexes, constraints and isolation levels | Nguyễn Duy Hiếu | Done | Sprint 1 | 10-Jun-2026 | Used EF Core Code-First Migrations
5 | Design | Technical Documentation (SRS/SDS) | System | Drafting Software Requirements and Software Design Specifications | Nguyễn Mạnh Hưng | Done | Sprint 1 | 12-Jun-2026 | Completed system topologies
6 | DevOps | CI/CD Deployment | System | Auto build/test on Github Actions; deploy backend to Railway and Frontend to Firebase | Nguyễn Duy Hiếu | Done | Sprint 1 | 14-Jun-2026 | Implemented workflow yaml with Gitleaks scan
7 | Authentication | Login (JWT) | All Roles | User attempts to log in via JWT token (email/password) | Nguyễn Mạnh Hưng | Done | Sprint 2 | 16-Jun-2026 | Implemented BCrypt and JWT provider
8 | Authentication | Google Auth SSO | Driver | Driver logs in / registers using Google OAuth Single Sign-on | Nguyễn Mạnh Hưng | Done | Sprint 2 | 18-Jun-2026 | Migrated to Google.Apis.Auth validation
9 | Frontend | Project Scaffold & UI Library | System | Setup Vite React, TailwindCSS, Router and Axios handlers | Nguyễn Quang Huy | Done | Sprint 2 | 19-Jun-2026 | Configured layout and component library
10 | Driver Module | Current Session UI | Driver | Live tile showing current parking session, location (floor/slot), entry time | Nguyễn Quang Huy | Done | Sprint 3 | 22-Jun-2026 | Used React interval to refresh fee simulation
11 | Driver Module | Wallet Top-Up UI | Driver | Integration of PayOS QR generation and top-up UI workflow | Nguyễn Quang Huy | Done | Sprint 3 | 24-Jun-2026 | Implemented polling for payment success status
12 | Driver Backend | Wallet PayOS Webhook | System | Handle PayOS webhooks for payment success verification | Nguyễn Duy Hiếu | Done | Sprint 3 | 25-Jun-2026 | Idempotency handling and balance updates
13 | Driver Module | Active Bookings UI | Driver | User interface for reserving parking slots ahead of time | Nguyễn Quang Huy | Done | Sprint 4 | 26-Jun-2026 | Handled double-booking bug on frontend
14 | Driver Backend | Booking Engine APIs | System | API endpoints and background expiry service for reservations | Nguyễn Mạnh Hưng | Done | Sprint 4 | 28-Jun-2026 | Reservation expiration CRON job created
15 | Driver Module | Monthly Pass Subscriptions | Driver | Subscription purchase and viewing interface | Trần Thái Bình | Done | Sprint 5 | 05-Jul-2026 | Frontend design for monthly passes
16 | Driver Backend | Subscription API & Pricing | System | Pricing calculation bypass for subscribers, billing API | Nguyễn Duy Hiếu | Done | Sprint 5 | 10-Jul-2026 | Added subscription waiver logic
17 | Staff Module | Slot Map Visualiser UI | Staff | Real-time slot grid with cell colors (Occupied/Available) | Nguyễn Quang Huy | Done | Sprint 3 | 20-Jun-2026 | Figma Design implemented in React
18 | Staff Backend | SignalR Real-Time Comm | System | Setup SignalR Hub to broadcast slot activity | Nguyễn Mạnh Hưng | Done | Sprint 3 | 22-Jun-2026 | Created broadcast groups logic (all, operations)
19 | Staff Backend | Check-In Processing | Staff | Atomic transaction for check-in: slot assigned, session initiated | Nguyễn Duy Hiếu | Done | Sprint 3 | 24-Jun-2026 | Uses Serializable transactions. Prevents duplicates.
20 | Staff Backend | Check-Out Processing | Staff | Calculate final fee based on duration/grace period; release slot | Nguyễn Duy Hiếu | Done | Sprint 3 | 25-Jun-2026 | Integrated with fee calculator rules (e.g. lost ticket)
21 | Staff Module | Camera OCR Integration | Staff | PaddleOCR server implementation for license plate scanning | Trần Thái Bình | Done | Sprint 4 | 10-Jul-2026 | Python PaddleOCR wrapper + PlateRecognizer fallback fallback
22 | Staff Module | Check-in Booking Auto-Redeem | Staff | UI modifications to auto-fetch booking and Backend API support | Nguyễn Mạnh Hưng | Done | Sprint 5 | 24-Jul-2026 | Auto mapped by frontend calling by-plate API before check-in
23 | Staff Module | Incident Logging UI/UX | Staff | Form for staff to create and track rule violations (e.g. lost ticket) | Trần Thái Bình | Done | Sprint 5 | 15-Jul-2026 | Assisted in frontend binding
24 | Manager Module | Dashboard KPIs Setup | Manager | Overall building usage, daily revenue sums, number of active sessions | Nguyễn Mạnh Hưng | Done | Sprint 5 | 16-Jul-2026 | Implemented snapshot DB queries
25 | Manager Module | Dashboard UI Charts | Manager | Implemented Recharts for 30-day analytics and floor density | Nguyễn Quang Huy | Done | Sprint 5 | 18-Jul-2026 | React-based interactive components
26 | Admin Module | Zone & Slot Setup | Admin | Define floors, zones, vehicle type constraints, base price policies | Nguyễn Duy Hiếu | Done | Sprint 1 | 30-May-2026 | CRUD ops provided via DatabaseSeeder base
27 | Security | Rate Limiting & CORS | System | Defend auth endpoints against brute force; lockdown origin access | Nguyễn Duy Hiếu | Done | Sprint 4 | 10-Jul-2026 | Applied standard .NET middlewares
28 | Documentation | Testing Report & UML | System | Full end-to-end testing, UML refactoring and Test cases generation | Trần Thái Bình | Done | Sprint 5 | 20-Jul-2026 | Verified UI tests and PaddleOCR stability
29 | Documentation | User Manual & Presentations | System | Finalising slides and operation instructions for the evaluation board | Nguyễn Mạnh Hưng | Done | Sprint 5 | 23-Jul-2026 | Assisted by Trần Thái Bình