## 1. Issue Register
ISSUES REPORT
Parking Building Management System (PBMS) — SU26SWP08
Project Code |  | SU26SWP08
Document Type |  | Issues Report (Template 4)
Version |  | 1.1
Period |  | Sprint 1 – Sprint Final (June – July 2026)
Prepared By |  | SU26SWP08 Development Team
1. Issue Register
Issue ID | Title | Category | Severity | Status
ISS-001 | Concurrent check-in double slot assignment | Transaction | Critical | Resolved
ISS-002 | PaddleOCR exception on Linux target | Integration | High | Resolved
ISS-003 | PayOS signature mismatch | Integration | High | Resolved
ISS-004 | Google Auth inactive on production hosting | Configuration | High | Resolved
ISS-005 | SignalR broadcast failure to Driver client | Realtime | Medium | Resolved
ISS-006 | Reservation auto-expiry scheduler error | Background | Medium | Resolved
ISS-007 | Zero fee charged for exactly 1-hour session | Logic | Medium | Resolved
ISS-008 | EWallet double deduction condition | Transaction | Critical | Resolved
ISS-009 | Cross-Origin (CORS) policy block | Configuration | High | Resolved
ISS-010 | Manager dashboard timestamp offset | UI | Low | Resolved
ISS-011 | Ticket lookup intuitively triggered checkout | UX/Logic | Medium | Resolved
ISS-012 | Slot map checkout bypassed confirmation | UX/Logic | High | Resolved
ISS-013 | Double booking on spam click | Transaction | Medium | Resolved
ISS-014 | Check-in did not auto-redeem reservation | Logic | High | Resolved

## 2. Issue Resolution Details
2. Issue Resolution Details
Issue ID | Title | Description | Root Cause | Resolution | Affected Components | Status
ISS-001 | Concurrent check-in double slot assignment | Simultaneous check-in requests generated duplicate Active session records for a single slot ID over separate threads. | Database read/write isolated under lower isolation bounds, allowing dirty reads. | Implementation of explicit ExecuteInTransactionAsync(IsolationLevel.Serializable) around the check-in data context scope. | ParkingSessionService.cs | Resolved
ISS-002 | PaddleOCR exception on Linux target | Platform threw DllNotFoundException when deployed to Linux nodes. | PaddleInference requires native Windows .dll build definitions not present in target environment. | Bound implementation to OperatingSystem.IsWindows(); injected stub service for Linux runtimes. Added web-based fallback endpoint parameters. | LocalOcrEngine.cs | Resolved
ISS-003 | PayOS Webhook Checksum Validation | Incoming webhooks systematically failed HMAC validation routines. | Payload object properties serialized to string incorrectly (order mismatch). | Implemented custom payload flattening to sort keys alphabetically as required by PayOS security standards prior to computation. | PayOsWebhookController.cs | Resolved
ISS-005 | SignalR Hub Group Assignment | Slot map failed to trigger state updates on the Driver's viewport automatically. | Driver connections lacked inclusion in the correct target broadcast group mapping. | Appended explicit Groups.AddToGroupAsync assignment in the Hub configuration for authenticated standard users. | ParkingHub.cs | Resolved
ISS-011 | Ticket lookup intuitively triggered checkout | Searching for a ticket code immediately checked the car out without confirming the fee. | The handleSearchTicket handler invoked the checkout API via processPlate directly. | Refactored to fetch session details and open a Checkout Confirmation Modal to review fees and payment methods. | StaffDashboard.tsx | Resolved
ISS-012 | Slot map checkout bypassed confirmation | Clicking on an occupied slot in the dashboard immediately checked the car out. | onClick handler triggered checkout instead of merely selecting the slot. | Removed auto-checkout on slot click. Added checkout flow via a detail panel and a confirmation modal. | StaffDashboard.tsx, ParkingSlotMap.tsx | Resolved
ISS-013 | Double booking on spam click | Driver users could book duplicate reservations for the same license plate if they spam clicked. | Reservation UI lacked a submit guard and backend lacked a unique plate check. | Added useRef-based submit guards on Frontend and added active reservation limits/duplicate checks on Backend API. | UserMobileHome.tsx, ReservationService.cs | Resolved
ISS-014 | Check-in did not auto-redeem reservation | When a reserved vehicle arrived, scanning the plate would create a new standard checkin, ignoring the booking. | Checkin flow did not cross-reference pending reservations for the scanned plate. | Created a by-plate reservation lookup API and automated the match in the staff UI during check-in. | StaffDashboard.tsx, ReservationsController.cs | Resolved

## 3. Discovered Limitations
3. Discovered Limitations
Limitation ID | Component | Description
LIM-001 | OCR Engine | Initial PaddleOCR library initialization blocks the main thread for 8-12 seconds on the primary call. A background warmup sequence was deployed to mitigate latency post-startup.
LIM-002 | Report Generation | Execution of snapshot generation requires manual administrator trigger due to omission of automated CRON scheduling logic in standard builds.
LIM-003 | Email Notification | Currently SMTP emailing for subscription expiry uses a synchronous task block. Recommended moving to background Queue channel.